## Milestones
ID | Activities | Dependency | Start Date | Scheduled End Date | Completion | Type | Task Owner | Description
1 | Planning |  | 2022-07-20 | 2022-07-21 | 100% | Milestone | Entire Group | An idea is born! A concept document (usually in a form of a 5-20 slide presentation) is created and pitched to key stakeholders. If the project is given the go-ahead, the initial preproduction team is assembled and tasked with expanding the concept. A crucial period where the most important design decisions are likely to be made. Core gameplay mechanics are being validated by prototyping. The game's scope, art direction, technical requirements, production schedule, and team size are all being established. At the end of preproduction, the GDD should be finalized by the designer and approved by key stakeholders.
2 | Interim | 1 | 2022-07-21 | 2022-07-25 | 100% | Milestone | Entire Group | Depending on the length of the project, several interim production milestones are usually set, with the aforementioned Vertical Slice often being one of them. These give the team a defined mid-term goal to work towards and are useful even if there is no publisher (and therefore payment) associated with them.
3 | Finalization | 2 | 2022-07-26 | 2022-07-27 | 100% | Milestone | Entire Group | At the end of the Alpha stage, the product should be feature-complete, meaning the game is playable from start to finish (should it have one) with all functionalities and content roughly in place. That said, the quality will be far from final, with many bugs left to be fixed and various improvements and changes to be made, often based on the results of playtesting. Beta represents a much more complete version of the game. In theory, all of the content is locked in place and the only changes being made from there on are bug fixes, balancing changes, tweaks, and polishing. Some companies will conduct public beta tests that are either closed (invite only) or open to everyone.
4 | Submission | 3 | 2022-07-27 |  | 100% | Milestone | Entire Group | It's time to celebrate! Your game has beaten the odds! Making games is hard and expensive, and the vast majority never see the light of day.

## Weekly Core Hours
Weekly Core Hours
Summer'22
| Monday | Tuesday | Wednesday | Thursday | Friday
9:00 | Morning Announcement
9:30 | 9:30am- 12:30pm | 9:30am- 12:30pm | 9:30am- 12:30pm | 9:30am- 12:30pm | 9:30am- 12:30pm
10:00
10:30
11:00
11:30
12:00
12:30 | Lunch
13:00
13:30 | 1:30pm- 4:30pm | 1:30pm- 4:30pm | 1:30pm- 4:30pm | 1:30pm- 4:30pm | 1:30pm- 4:30pm
14:00
14:30
15:00
15:30
16:00
16:30 | Evening Attendance
17:00
17:30
18:00
18:30
19:00
19:30
20:00

## Game Design
Task | Type | Description | Deadline | Priority | Progress | Owner | Design Guide | Notes | Links
Complete inital game design document | Concept | Have a team meeting and brainstorm game concepts | 2022-07-20 | Planning | Complete | All
Complete new version of design document | Concept | Update original game design document | 2022-07-21 | Planning | Complete | All |  |  | https://docs.google.com/document/d/1V4S8juc-2lBPcK6sSZanOHHbJxDWmJ2xEqTbnv3Y-iM/edit#
Physical prototype | Concept | Create a physical prototype that shows basics of game | 2022-07-23 | Planning | Complete | All |  |  | https://drive.google.com/file/d/1z5kYjg1CCFFTHfGrFPx14sOpiwSSzyoV/view?usp=sharing
Interim Presentation | Main Feature | Create presentation with concept art, sound demos, game design discussion, programming, production, and interim prototype that showcases game | 2022-07-24 | Interim | Complete | All
Final Presentation | Main Feature | Create presentation with final art, final sound, final code, and final build | 2022-07-27 | Finalization | Complete | All
Score system | Main Task | Scoring system after identities are found | Week 12 | Alpha | Done | Jeffrey
Search Assignment Generation Algorithm | Main Task | algorithm to generate which identity the player should search for, one after another | Week 12 | Alpha | Done | Jeffrey | GDD 4 Catch me if you can
Generate bots | Sub Task | Generate 300 bots to help test gameplay | Week 13 | Beta | QA | Jeffrey
Update Report | Main Task | Make report for visual | Week14 | Beta | Not Started | Jeffrey
Team Auto Generation | Sub Task | The composition of each team is balanced by a calculation of players’ similarities. The algorithm needs to be specified. The tentative team size is 2-8. Playtest needed. Team size might increase throughout rounds of puzzles. Rules TBD. | Week 10 | Alpha | QA | Chao | GDD 4. Solve Puzzles (Cooperation) --> 4.1 Team Size (room size) | Jeffrey is working on the algorithm
Puzzle Auto Generation | Sub Task | The attributes and number requirements of the puzzles are generated automatically based on the compositions of the players on the team. E.g, if there are five players who have the “Jazz” attribute, then the number of Jazz required in this puzzle should be less than 5. I.e., the program always makes sure the puzzle is solvable and requires all members’ input. | Week 10 | Alpha | QA | Jeffrey | GDD 4. Solve Puzzles (Cooperation) --> 4.2 Puzzle Generation Rules | Jeffrey is working on the algorithm
Wrap Up Personal Report (MVP) | Main Task | design review; one swipe, one page down; fix default numbers | Week 11 | Alpha | In Progress | Jeffrey | GDD 5. Wrap-up (Data-oriented) --> 5.1 Personal Report
Player Spawn Distribution | Sub Task | The distribution of the players affects their starting place in the space and who the players will first meet. The distribution is balanced by a calculation of players’ similarities. The algorithm needs to be specified. | Week 11 | Alpha | In Progress | Chao | GDD 3. Exploration --> 3.4 Distribution
Tutorial | Main Task | Add tutorial images before gameplay | Week 11 | Alpha | QA | Amber

## Programming
Task | Type | Description | Deadline | Priority | Progress | Owner | Design Guide | Notes | Links
Create a Unity project | Main Task | Create a 2D Unity project | 2022-07-21 | Planning | Complete | All
Q*Bert Programming Design Doc | Sub Task | Plan classes and methods | 2022-07-20 | Planning | Complete | All |  |  | https://docs.google.com/document/d/14j0_tXF6XdwFla200er2-OT1-4SW-jRUxrwS3Id593E/edit
Player Movement | Main Task | Make the player move like it does in Q*Bert, includes control scheme (WASD) | 2022-07-23 | Interim | Complete | Yichen
Map | Main Task | Build map (pending idea: blocks change colors) | 2022-07-23 | Interim | Complete | Vivian
Game over scene | Sub Task | Session score, the session level reached, and Play Again button | 2022-07-23 | Interim | Complete | Vivian
Purple frog | Main Task | Goes downwards and randomly chooses which block to jump on, can't be killed, doesn't revert progress | 2022-07-23 | Interim | Complete | Vivian
Death system | Main Task | Implement player death, game over scene | 2022-07-23 | Interim | Complete | Yichen
Put in test background music and menu music | Sub Task | Put in BGM part 1 and part 2 (loop part 2), put in Menu Music | 2022-07-24 | Interim | Complete | Vivian
Caveman | Main Task | Follows player, doesn't revert progress, can't be killed | 2022-07-23 | Interim | Complete | Vivian
Dodo Bird | Main Task | Can be killed by player, same movement as purple frog, reverts progress | 2022-07-23 | Interim | Complete | Vivian
Life System | Main Task | Add life system, lose three lives = game over | 2022-07-23 | Interim | Complete | Yichen
Void Death | Main Task | Add death if you walk off the edge of level | 2022-07-23 | Interim | Complete | Yichen
UI System | Main Task | Includes: points, life count, current goal (what color block you need) | 2022-07-23 | Interim | Complete | Vivian
Put in SFX drafts | Main Task | Main menu, gameplay, and game over | 2022-07-24 | Interim | Complete | Vivian
Backgrounds | Sub Task | Implement cave and clouds | 2022-07-24 | Interim | Complete | Yichen
Player animations | Main Task | Implement player animations (jump, and hit/roaring (open mouth)) | 2022-07-27 | Finalization | Complete | Yichen
Enemy animations | Main Task | Implement enemy animations (frog (legs), dodobird (flap), and Cavebert (breaks out of boulder, legs), dodobird (death) | 2022-07-27 | Finalization | Complete | Vivian
Disk | Main Task | Add disk (pteradactyl) that brings T-bert to top of playspace, implement animations | 2022-07-26 | Finalization | Complete | Yichen
Updated Cavebert behavior | Main Task | Spawn from bottom from boulder, roll from top, fall off when on disk | 2022-07-26 | Finalization | Complete | Vivian
Updated UI | Main Task | Add current round, quit button, main menu button, improved score font, on screen displayed controls, enemy spawn indicators | 2022-07-27 | Finalization | Complete | Vivian
Score system | Main Task | Scoring system after identities are found | Week 12 | Alpha | Done | Jeffrey
Search Assignment Generation Algorithm | Main Task | algorithm to generate which identity the player should search for, one after another | Week 12 | Alpha | Done | Jeffrey | GDD 4 Catch me if you can
T-bert Respawn | Main Task | Make T-bert respawn at last location after being hit instead of spawning at top | 2022-07-26 | Finalization | Complete | Yichen
Updated buttons | Sub Task | Allow player to additionally click mouse at Game Over to head back to main menu | 2022-07-26 | Finalization | Complete | Vivian
Updated background | Main Task | Implement updated background from artists, add cloud movement to main menu as well, ground the mountain | 2022-07-27 | Finalization | Complete | Yichen
Updated controls | Main Task | Allow arrow keys to be used alongside WASD | 2022-07-26 | Finalization | Complete | Yichen
Enemy Pacing/Flow | Sub Task | Optimize enemy spawning, too easy, too overwhelming, difficulty increases every 5 rounds (faster spawns, till 10 rounds, then constant) | 2022-07-27 | Finalization | Complete | Yichen
Updated audio | Main Task | Test new audio, implement (have audio designer help balance) new SFX and music tracks | 2022-07-27 | Finalization | Complete | Vivian
Team Auto Generation | Sub Task | The composition of each team is balanced by a calculation of players’ similarities. The algorithm needs to be specified. The tentative team size is 2-8. Playtest needed. Team size might increase throughout rounds of puzzles. Rules TBD. | Week 10 | Alpha | QA | Chao | GDD 4. Solve Puzzles (Cooperation) --> 4.1 Team Size (room size) | Jeffrey is working on the algorithm
Puzzle Auto Generation | Sub Task | The attributes and number requirements of the puzzles are generated automatically based on the compositions of the players on the team. E.g, if there are five players who have the “Jazz” attribute, then the number of Jazz required in this puzzle should be less than 5. I.e., the program always makes sure the puzzle is solvable and requires all members’ input. | Week 10 | Alpha | QA | Jeffrey | GDD 4. Solve Puzzles (Cooperation) --> 4.2 Puzzle Generation Rules | Jeffrey is working on the algorithm
Wrap Up Personal Report (MVP) | Main Task | design review; one swipe, one page down; fix default numbers | Week 11 | Alpha | In Progress | Jeffrey | GDD 5. Wrap-up (Data-oriented) --> 5.1 Personal Report
Player Spawn Distribution | Sub Task | The distribution of the players affects their starting place in the space and who the players will first meet. The distribution is balanced by a calculation of players’ similarities. The algorithm needs to be specified. | Week 11 | Alpha | In Progress | Chao | GDD 3. Exploration --> 3.4 Distribution
Tutorial | Main Task | Add tutorial images before gameplay | Week 11 | Alpha | QA | Amber

## Art
Task | Type | Description | Deadline | Priority | Progress | Owner | Design Guide | Notes | Links
Sketch player | 2D | Sketch 2D sprite of the main character | 2022-07-21 | Planning | Complete | All
Concept art | 2D | Create concept art of character, location, walking on blocks, and enemies | 2022-07-24 | Planning | Complete | All
Color pallete | 2D | Choose main colors for game | 2022-07-20 | Planning | Complete | Danny | Easy to see, easy for the eyes. |  | https://drive.google.com/drive/u/6/folders/1DAl34S51LHZudJGOxJhgiZoPQTViCZSR
Final player | 2D | Create player, all 4 sides | 2022-07-22 | Interim | Complete | Danny
Purple Frog | 2D | Create purple frog, all 4 sides | 2022-07-22 | Interim | Complete | Alex
Blocks | UI | Create blocks/tiles | 2022-07-22 | Interim | Complete | Danny
Background | UI | Cube mountain | 2022-07-23 | Interim | Complete | Alex
Dodobird | 2D | Dodo bird, all 4 sides | 2022-07-24 | Interim | Complete | Alex
Cavebert | 2D | Cavebert, all 4 sides | 2022-07-24 | Interim | Complete | Alex
Cloud background | UI | Scenic cloud background, "loopable" | 2022-07-23 | Interim | Complete | Danny
Game over art | UI | Press any key to start, Game Over text | 2022-07-23 | Interim | Complete | Alex
Main menu art | UI | Logo (T-bert), start button | 2022-07-24 | Interim | Complete | Danny
UI Elements | 2D | Includes: text for... points, life count, current goal (what color block you need) | 2022-07-24 | Interim | Complete | All
Player animations | 2D | Animations for main player (jump (dust after jump), roaring (open mouth)) | 2022-07-27 | Finalization | Complete | Danny
Enemy animations | 2D | Animations for frog (legs extend), dodobird (flap), and Cavebert (breaks out of boulder, legs) | 2022-07-27 | Finalization | Complete | Alex
Final mechanics | 2D | disks (pteradactyl, fly animation) (Danny), Cavebert boulder (Alex) (boulder, bounce animation), dodobird death animation (Alex) | 2022-07-27 | Finalization | Complete | All
Controls UI | UI | Displayed controls (for WASD, have arrow direction with corresponding letter) | 2022-07-26 | Finalization | Complete | Danny
Quit button, and main menu button | UI | Custom made quit and main menu button, similar to start button | 2022-07-26 | Finalization | Complete | Danny
Updated background | 2D | Add more jungle theming, trees, blend mountain with ground, keep the clouds | 2022-07-26 | Finalization | Complete | Alex
Score system | Main Task | Scoring system after identities are found | Week 12 | Alpha | Done | Jeffrey
Search Assignment Generation Algorithm | Main Task | algorithm to generate which identity the player should search for, one after another | Week 12 | Alpha | Done | Jeffrey | GDD 4 Catch me if you can
Generate bots | Sub Task | Generate 300 bots to help test gameplay | Week 13 | Beta | QA | Jeffrey
Update Report | Main Task | Make report for visual | Week14 | Beta | Not Started | Jeffrey
Team Auto Generation | Sub Task | The composition of each team is balanced by a calculation of players’ similarities. The algorithm needs to be specified. The tentative team size is 2-8. Playtest needed. Team size might increase throughout rounds of puzzles. Rules TBD. | Week 10 | Alpha | QA | Chao | GDD 4. Solve Puzzles (Cooperation) --> 4.1 Team Size (room size) | Jeffrey is working on the algorithm
Puzzle Auto Generation | Sub Task | The attributes and number requirements of the puzzles are generated automatically based on the compositions of the players on the team. E.g, if there are five players who have the “Jazz” attribute, then the number of Jazz required in this puzzle should be less than 5. I.e., the program always makes sure the puzzle is solvable and requires all members’ input. | Week 10 | Alpha | QA | Jeffrey | GDD 4. Solve Puzzles (Cooperation) --> 4.2 Puzzle Generation Rules | Jeffrey is working on the algorithm
Wrap Up Personal Report (MVP) | Main Task | design review; one swipe, one page down; fix default numbers | Week 11 | Alpha | In Progress | Jeffrey | GDD 5. Wrap-up (Data-oriented) --> 5.1 Personal Report
Player Spawn Distribution | Sub Task | The distribution of the players affects their starting place in the space and who the players will first meet. The distribution is balanced by a calculation of players’ similarities. The algorithm needs to be specified. | Week 11 | Alpha | In Progress | Chao | GDD 3. Exploration --> 3.4 Distribution
Tutorial | Main Task | Add tutorial images before gameplay | Week 11 | Alpha | QA | Amber

## Sound
Task | Type | Description | Deadline | Priority | Progress | Owner | Design Guide | Notes | Links
Plan needed sound effects | SFX | List out sounds needed for game | 2022-07-20 | Planning | Complete | Kristijan |  | Player jump, frog, caveman, dodo bird, game over, button sound, falling into the void, success for beating a level, losing life
Sound Effects Draft | SFX | Compose draft sound effects | 2022-07-23 | Interim | Complete | Kristijan |  | Use Bfxr
Draft BGM | BGM | Compose a draft BGM that can be looped in the game | 2022-07-22 | Interim | Complete | Kristijan |  | 16-bit prehistoric, funky, retro background music. Make the player feel like they’re on an adventure in the jungle.
Menu Music Draft | BGM | Compose a menu music that can be looped in the game main menu start screen | 2022-07-23 | Interim | Complete | Kristijan |  | Starts up on main menu, has two parts
T-bert SFX | SFX | Updated falling sound effect (more characterized), updated swear/hit audio | 2022-07-26 | Finalization | Complete | Kristijan |  | Use Vocal Playground
Updated SFX | SFX | Dodobird jump, level success (drums don't fit, needs rework), T-bert jump | 2022-07-26 | Finalization | Complete | Kristijan
New SFX | SFX | Killing dodobird, dying Cavebert, disk (pteradactyl) | 2022-07-26 | Finalization | Complete | Kristijan
Balance SFX | SFX | Raise volume of more important sounds, reduce volume of less important sounds, create balance | 2022-07-27 | Finalization | Complete | Kristijan
Game Over Music | BGM | Create a game over music composition | 2022-07-27 | Finalization | Complete | Kristijan |  | More somber, maintain similar instruments
Updated Gameplay BGM | BGM | Get rid of buildup (make it flow from menu), more unique | 2022-07-27 | Finalization | Complete | Kristijan